## Sheet1
TO-DO-LIST APP
Project Start : Wednesday Janurary 23rd, 2025
Group Members: Jimmy Nguyen, Samantha Treasure, Brett Lewis, Jasiah Peppers |  |  |  |  | Janurary 20, 2025 | [6 empty] | Janurary 27, 2025 | [6 empty] | Janurary 20, 2025
[5 empty] | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2
[5 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | S | S | S | S
TASK | ASSIGNED TO | PROGRESS | START | END
Milestone 1
Ganatt Chart Layout | Jimmy Nguyen | 80% | 2025-01-23 | 2025-01-25 | bar: Janurary 20, 2025 23 T to Janurary 20, 2025 25 S
Video Editting | Samantha Treasure | 90% | 2025-01-23 | 2025-01-26 | bar: Janurary 20, 2025 23 T to Janurary 20, 2025 26 S
Solo Recording | Jimmy Nguyen | 100% | 2025-01-23 | 2025-01-25 | bar: Janurary 20, 2025 23 T to Janurary 20, 2025 25 S
Solo Recording | Samantha Treasure | 100% | 2025-01-23 | 2025-01-25 | bar: Janurary 20, 2025 23 T to Janurary 20, 2025 25 S
Solo Recording | Brett Lewis | 100% | 2025-01-23 | 2025-01-25 | bar: Janurary 20, 2025 23 T to Janurary 20, 2025 25 S
Solo Recording | Jasiah Peppers | 100% | 2025-01-23 | 2025-01-25 | bar: Janurary 20, 2025 23 T to Janurary 20, 2025 25 S
Milestone 2